## week1
Computer Science 2 Project | Team Members: | Esmeres, Chatzkel Cuddy
Group Progress Report |  | Malquisto, Xymon Keith E.
3rd Quarter
Week 1 - Jan 16, 2026
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
Cultivate questions and puzzles for quiz | We have puzzle questions for some | We have questions for different types of
| intelligences already | intelligence except a few
Create an algorithm for user scoring
specifically one that calculates for the
displaying of our polar bar chart
STRENGTH
We have questions for half of our
intelligences
AREAS FOR DEVELOPMENT
Making a GUI in Python
STRATEGY FOR SUCCESS
Play music to be motivated

## week2
Computer Science 2 Project | Team Members: | Esmeres, Chatzkel Cuddy
Group Progress Report |  | Malquisto, Xymon Keith E.
3rd Quarter
Week 2 - Jan 23, 2026
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
Create a menu |  | Done
Code the continuation of menu such |  | Almost done
as the showing of the quiz
STRENGTH
Currently we're testing an |  | We have created a separate program
implementation of a GUI |  | and its shown that the GUI works well
with the tkinter python library |  | so we just have to add it to our code
by the next or next next week we will
begin the implementation of it
AREAS FOR DEVELOPMENT
We are currently struggling in locating |  | Small progress however we have ~20%
effective puzzles that can be used for |  | of the amount of questions we need
the quiz since the questions must
deal with an important aspect of that
type of intelligence
STRATEGY FOR SUCCESS
We aim to focus on an effective addition
of our GUI to our code and search more
efficiently for plausible and effective
puzzles.

## week3
Computer Science 2 Project | Team Members:
Group Progress Report
3rd Quarter
Week 3 - Jan 30, 2026
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
STRENGTH
AREAS FOR DEVELOPMENT
STRATEGY FOR SUCCESS

## week4
Computer Science 2 Project | Team Members:
Group Progress Report
3rd Quarter
Week 4 - Feb 6, 2026
GOAL State your goal for the Week | DATA COLLECTED State/list the data collected relevant to your project | PROGRESS State the progress you have made so far by the end of the week
STRENGTH
AREAS FOR DEVELOPMENT
STRATEGY FOR SUCCESS